## Slide 1: Schedule Representation
Tasks | Duration (Days) | Dependencies
T1 | 10 | 
T2 | 5 | T1
T3 | 4 | T1
T4 | 6 | T2
T5 | 9 | T3
T6 | 5 | T4,T5

## Slide 2: Schedule Representation
Tasks | Duration (Days) | Dependencies
T1 | 10 | 
T2 | 5 | T1
T3 | 4 | T1
T4 | 6 | T2
T5 | 9 | T3
T6 | 5 | T4,T5
Path1: Start- T1-T2-T4-T6 –End=26 days
Path2: Start- T1-T3-T5-T6 –End=28 days

## Slide 3: Schedule Representation
Tasks | Duration (Days) | Dependencies
T1 | 10 | 
T2 | 5 | T1
T3 | 4 | T1
T4 | 6 | T2
T5 | 9 | T3
T6 | 5 | T4,T5
Path1: Start- T1-T2-T4-T6 –End=26 days
Path2: Start- T1-T3-T5-T6 –End=28 days
(Critical Path)

## Slide 4
4
Purpose of a Task Network
Also called an activity network
It is a graphic representation of the task flow for a project
It depicts task length, sequence, concurrency, and dependency
Points out inter-task dependencies to help the manager ensure continuous progress toward project completion
The critical path
  A single path leading from start to finish in a task network
  It contains the sequence of tasks that must be completed on schedule if the project as a whole is to be completed on schedule
  It also determines the minimum duration of the project
Notes: 4

## Slide 5
5
Example Task Network
Task A
3
Task B
3
Task E
8
Task F
2
Task H
5
Task C
7
Task D
5
Task I
4
Task M
0
Task N
2
Task G
3
Task J
5
Task K
3
Task L
10
Where is the critical path and what tasks are on it?
Notes: 5

## Slide 6
6
Example Task Network with Critical Path Marked
Task A
3
Task B
3
Task E
8
Task F
2
Task H
5
Task C
7
Task D
5
Task I
4
Task M
0
Task N
2
Task G
3
Task J
5
Task K
3
Task L
10
Critical path: A-B-C-E-K-L-M-N
Notes: 6

## Slide 7: Work Breakdown Structure
It represents a logical decomposition of the work to be performed and focuses on how the product, service, or result is naturally subdivided. It is an outline of what work is to be performed.

## Slide 8
8
40-20-40 Distribution of Effort
A recommended distribution of effort across the software process is
  40% (analysis and design)
  20% (coding)
  40% (testing)‏
Work expended on project planning rarely accounts for more than 2 - 3% of the total effort
Requirements analysis may comprise 10 - 25%
  Effort spent on prototyping and project complexity may increase this
Software design normally needs 20 – 25%
Coding should need only 15 - 20% based on the effort applied to software design
Testing and subsequent debugging can account for 30 - 40%
  Safety or security-related software requires more time for testing
(More on next slide)‏
Notes: 8

## Slide 9
9
40-20-40 Distribution of Effort (continued)‏
Testing
Coding
Design
Analysis
P
6/1
6/4
6/23
7/14
8/2
9/5
40
20
40
Example: 100-day project
Notes: 9

## Slide 10: Developing WBS
The WBS Should Be Deliverable-Oriented
Ensure WBS allows for the delivery of all the project’s deliverables as defined in project scope
Developing the WBS should involve the people who will be doing the Work

## Slide 11: Example of WBS with Estimated Task Durations

## Slide 13: Example of WBS with Estimated Task Duration
6.2 Test Result Report
  6.2.1 Review test plan with client 1 day
  6.2.2 Carry out test plan 5 days
  6.2.3 Analyze result 2 days
  6.2.4 Prepare test result report &presentation 3 days
  6.2.5 Present test result to client 1 day
  6.2.6 Address any s/w issue or problem 5 days

## Slide 19
Timeline Chart
Notes: 19

## Slide 20: Task Network-Example of MIS

## Slide 21: Example of Gantt Chart

## Slide 22: Example of Gantt Chart

## Slide 23
23
Mechanics of a Timeline Chart
Also called a Gantt chart; invented by Henry Gantt, industrial engineer, 1917
All project tasks are listed in the far left column
The next few columns may list the following for each task: projected start date, projected stop date, projected duration, actual start date, actual stop date, actual duration, task inter-dependencies (i.e., predecessors)‏
To the far right are columns representing dates on a calendar
The length of a horizontal bar on the calendar indicates the duration of the task
When multiple bars occur at the same time interval on the calendar, this implies task concurrency
A diamond in the calendar area of a specific task indicates that the task is a milestone; a milestone has a time duration of zero
1
None
Pred.
3/1
3/1
0
Milestone N
2
2/28
1/1
2 months
Task A
1
Finish
Start
Duration
Task Name
Task #
Jan Feb Mar Apr May Jun Jul Aug Sep Oct
Notes: 23

## Slide 24
24
J
5/9
5/8
2
Install Inc Two
K
E
5/6
5/2
5
Install Inc One
F
E, I
5/7
5/2
6
Test Inc Two
J
A, B
4/13
4/7
7
Analyze Inc Two
G
F, K
H
G
D
C
B
A
None
Pred.
5/11
5/10
2
Close out project
L
4/22
4/19
4
Code Inc Two
I
4/18
4/14
5
Design Inc Two
H
5/1
4/22
10
Test Inc One
E
4/21
4/15
7
Code Inc One
D
4/14
4/7
8
Design Inc One
C
4/6
4/4
3
Analyze Inc One
B
4/3
4/1
3
Establish increments
A
Finish
Start
Duration
Task Name
Task #
A. Establish
Increments
3
B. Analyze
Inc One
3
C. Design
Inc One
8
D. Code
Inc One
7
F. Install
Inc One
5
G. Analyze
Inc Two
7
H. Design
Inc Two
5
I. Code
Inc Two
4
K. Install
Inc Two
2
L. Close out
Project
2
E. Test
Inc One
10
J. Test
Inc Two
6
4/1 4/8 4/15 4/22 4/29 5/6 5/13 5/20 5/27 6/3
Task network and the critical path:
Timeline chart:
SOLUTION
A-B-C-D-E-J-K-L
Notes: 24

## Slide 25: Timeline Charts
Work breakdown is input as a task network
Tasks are assigned to specific person
Consequence of this input is a Timeline chart also called a Gantt Chart
A timeline chart can be developed for the entire project
Separate charts can also be developed for each project function or for each individual working on the project

## Slide 26: Timeline Charts

## Slide 27: Project Tables/Resource Tables

## Slide 28: Tracking Schedule
Project Schedule provides a road map for software project manager
Tracking can be accomplished in the following ways:-
    Conducting periodic project status meetings in which each team member reports progress and problems
      Evaluating results of all reviews conducted throughout the software engineering process
      Determining whether formal project milestones have been accomplished by scheduled date

## Slide 29: Tracking Schedule
  Comparing actual start-date to planned start-date for each project task listed in the resource table
  Meeting Informing with practitioners to obtain their subjective assessment of progress to date and problems on the horizon
  Using earned value analysis to assess progress quantitatively

## Slide 30: Controlling the Project
Control is employed by a software project manager to administer project resources, cope with problems, and direct project staff
  If project is on schedule and within budget then control is light
  When problems occur, additional resources may be deployed. Example- staff may be redeployed, project schedule can be redefined
  When severe deadline pressure occurs, time boxing technique is used

## Slide 31: Contd…
Time Boxing
This strategy recognizes that the complete product may not be delivered by predefined deadline
An incremental software model is chosen and a schedule is derived for each incremental delivery
Schedule for each task is adjusted by working backward from the delivery date for the increment
A “box” is put around each task. When task hits boundary of box, works stops and next task begins

## Slide 32: Contd..
Time Boxing
By the time the boundary of time box is encountered, 90% of task has been completed
The remaining 10%
    can be delayed until next increment or
    can be completed later if required
Rather than becoming stuck on a task, the project proceeds towards delivery date

## Slide 33: Project Control Cycle

## Slide 34: Project Monitoring and Control
Monitoring –collecting, recording, and reporting information concerning project performance that project manger and others wish to know
Controlling –uses data from monitor activity to bring actual performance to planned performance

## Slide 35: What is to be monitored?
Inputs
  Time
  Money
  Resources
  Material Usage
  Tasks
  Quality/Technical Performance
Outputs
  Progress
  Costs
  Job starts
  Job completion
  Engineering / Design changes