## Slide 1: Function-Oriented Metrics
In 1977, A.J. Albrecht of IBM developed a method of software metrics based on functionality. He called it the function point.
Based of FP measure of software many other metrics can be computed
    Error/FP
    $/FP
    Defects/FP
    Pages of documentation/FP
    Errors/PM
    Productivity = FP/PM (Effort is measured in person-months)
    $/Page of Documentation
LOCs of an applications can be estimated from FP, they are interconvertible.
This process known as Backfiring.
Example: 1 FP = 100 lines of COBOL code

## Slide 2: Function-Oriented Metrics
Count no. of External Inputs (EI)
Count no. of External Outputs (EO)
Count no. of External Inquiries (EQ)
Count no. of Internal Logical Files (ILF)
Count no. of External Interface Files (EIF)

## Slide 3: Steps In Calculating FP
1 Count the measurement parameters.
2. Assess the complexity of the values i.e. whether a particular value is simple, average or complex.
3. Compute the FP using the formula:-
  FP = count total x [0.65 + 0.01* ]
  In Fi i value ranges from 1 to 14 obtained from 14 questions

## Slide 4: Function Oriented Metrics

## Slide 5: Value adjustment Factors
Does the system require reliable backup and recovery?
Are data communications required?
Are there distributed processing functions?
Is performance critical?
Will the system run in an existing, heavily utilized operational environment?
Does the system require on-line data entry?
Does the on-line data entry require the input transaction to be built over multiple screens or operations?
Are the master files updated on-line?
Are the inputs, outputs, files, or inquiries complex?
Is the internal processing complex?
Is the code designed to be reusable?
Are conversion and installation included in the design?
Is the system designed for multiple installations in different organizations?
Is the application designed to facilitate change and ease of use by the user?

## Slide 6: Example:-
Q) Consider a Safe Home System given below:
Calculate the Function Point.

## Slide 7: Solution:
Step-1
For a Safe Home System, the Weighting Factor is assumed to be Simple
This is unadjusted function point

## Slide 8: Step -2
Assign values to the 14 questions on a scale of 0 to 5.
  1. Backup & Recovery =4
  2. Data communications=2
  3. Distributed Processing=2
  4. Performance Critical=4
  5. Existing Operating Environment=4
  6. Online Data entry=3
  7. Input transaction over multiple screens=2
  8. Master Files updated Online=5
  9. Information domain values Complex=3
  10. Internal Processing Complex=3
  11. Code designed for reuse=3
  12. Conversion/Installation in design=4
  13. Multiple Installations=4
  14. Application designed for change=3
Total value adjustment factor=Σ Fi=46

## Slide 9: Step-3
FP=count total * [ 0.65 + 0.01 * Σfi ]
=50 * [0.65+0.01*46]
=50 * [0.65+0.46]
=50 * 1.11
=55.5
=56 (FP is always rounded off to nearest integer value)

## Slide 10: Example 2: Consider a Railway Reservation System given below:
Calculate the Function Point.

## Slide 11: Solution:-
Step-1
For a Railway Reservation System, the Weighting Factor is assumed to be Average
Average

## Slide 12: Step -2
Assign values to the 14 questions on a scale of 0 to 5.
  1. Backup & Recovery =5
  2. Data communications=4
  3. Distributed Processing=4
  4. Performance Critical=4
  5. Existing Operating Environment=3
  6. Online Data entry=3
  7. Input transaction over multiple screens=4
  8. Master Files updated Online=3
  9. Information domain values Complex=2
  10. Internal Processing Complex=3
  11. Code designed for reuse=4
  12. Conversion/Installation in design=5
  13. Multiple Installations=3
  14. Application designed for change=3
  Total value adjustment factor=Σ Fi=50

## Slide 13: Step-3
FP=count total * [ 0.65 + 0.01 * Σfi ]
=64 * [ 0.65 + 0.01 * 50 ]
=64 * [ 0.65 + 0.5 ]
=64 * 1.15
=73.6
=74

## Slide 14: Example 3: Find Function Point for a complex system and calculate the Cost and Effort for the given system. Given Labour rate is $7000 per person-month and Cost per Function Point is $1500.
    No. of user inputs 15
    No. of user outputs 10
    No. of user inquiries 15
    No. of files 10
    No. of external files 8
Solution:- Step-1 : The Weighting Factor is assumed to be Complex

## Slide 15: Step -2
Assign values to the 14 questions on a scale of 0 to 5.
  1. Backup & Recovery =5
  2. Data communications=5
  3. Distributed Processing=5
  4. Performance Critical=4
  5. Existing Operating Environment=5
  6. Online Data entry=3
  7. Input transaction over multiple screens=3
  8. Master Files updated Online=4
  9. Information domain values Complex=5
  10. Internal Processing Complex=4
  11. Code designed for reuse=4
  12. Conversion/Installation in design=5
  13. Multiple Installations=5
  14. Application designed for change=5
Total value adjustment factor=Σ Fi=62

## Slide 16
Step-3
    FP=count total*[0.65+0.01*ΣFi]
    =480*[0.65+0.01*62]
    =480*[0.65+0.62]
    =480*1.27
    =609.6
    =610
Step-4
    Cost=FP* Cost Per Function Point
    Total estimated cost = 610*1500
    =$915000
    Effort=Estimated Cost/Labour Rate
    Total estimated effort=915000/7000
    =130.71
    =131 person months

## Slide 17: FP based Estimation-example
Calculate FP for a system, on the basis of following information
  S= (Sopt+4Sm+Spess)/6

## Slide 18: FP based Estimation-example
Solution
  S= (Sopt+4Sm+Spess)/6

## Slide 19: FP based Estimation-example
  FP = count total x [0.65 + 0.01 x summation of Fi]
  In Fi i value ranges from 1 to 14 obtained from 14 questions

## Slide 20: FP based Estimation-example
Total = 52

## Slide 21: Process based Estimation

## Slide 22: Process-Based Estimation
Use-Case Based Estimation

## Slide 23: Process based Estimation-example (use case based)
Historical data or
Average Data
Actual Data

## Slide 24: Use case based Estimation-example

## Slide 25
a) Differentiate between FP based & LOC based cost estimation techniques. (10)